## Slide 1: IPAC’26 Status report
Hanna Franberg-Delahaye
Local Organising Chair

## Slide 2: Registrations Monday at 14:00
Female | Male | Totale | Paiements done
88 | 245 | 333 | 108
Scientific | Students | EPS members | Accompanying | Exhibitor extra
221 | 37 | 21 |  | 11
15 printed versions
Cocktail Tuesday, Banquet Thursday: 319
84 invitation letter for VISA
100-113 lunches
80 bus tickets from Paris- Deauville Saturday/Sunday
40 bus tickets Deauville-Paris
Visites
SOLEIL: 46
ESRF: 9
GANIL: 51

## Slide 3: What to expect next couple of weeks:
18 Mars:
Changement tarif
Recencer les horaires de vols plannifiers les nombres de bus.

## Slide 4
Posters to be sent
2025
Jan.
Feb.
May
April
1st announcement of IPAC26 to the industry
Creation of registration and payment forms
Contracting for accommodations
June
Jul.
Sep.
Oct.
Website online
Nov.
Dec.
Deadline for submission of abstracts, grant applications and awards.
JACoW Meeting
Invitation from the editorial team - JACOW
Registration opens
+
Abstract submissions
16
2024
Nov.
Formation of the SAB
Dec.
Classification in INDICO
Call for oral contributions
LOC
PCO
SPC
Summary programme +
Letter to the invited speakers
SPC2
2 distance and 1 in Taipei
Selection of the featured speakers referred to as 'invited'
Website ready
Finalisation of the site for registrations and payments + tests
LOC Meetings In-Person (April, September?)
Contr.
Transport
Sites
Caterers

## Slide 5
Information on future accelerator projects
May
2026
Jan.
Feb.
April
June
July
March
SPC3 Meeting – selection of oral presentations and session chairs
Validation of the programme
Decision on the number of student grants
Preparation of the awards
Announcement of the awards
Announcement of the posters
Announcement of the student grants
Downloading of contributions
Contracting PCs for editing and others
Creation of edited documents
Number of posters per day.
Assignment of codes (presentations, posters…)
Invitations to various VIPs
IPAC’26
Submission of the proceedings
Set up the site
Publication of the proceedings 'pre-press'
Debriefing notes
LOC meetings
24
End of Early-Bird
1st confirmation of estimated catering numbers
Finalise the bus numbers
First release of hotel rooms
LOC
PCO
SPC
Finalise the ceremonies:
of openings
Price
Closure
Budget closing
REX GANIL
Define evening animations
Programme validation
……..
FAIT
FAIT
FAIT
FAIT
FAIT
FAIT
FAIT
Encours
FAIT
FAIT
Encours
Encours

## Slide 6: IPAC Booklets
CONFERENCE GUIDE
PARTICLE ACCELERATOR
BOOKLET
+ Booklet
Student session and poster présentations
A questionnaire will be sent in a week or two to all laboratories.
In electronic PDF version.
+ printed copies can be ordered at the registration
Same chapters and structure as IPAC’23

## Slide 7: Badge
Hanna
FRANBERG DELAHAYE
GANIL, FRANCE

## Slide 8: Pocket guide Short Program and information folder

## Slide 9: Register flow on INDICO
Indico
Confirmation and Payment
Manual verification if wire transfer
Indico
If modification manual modification
******
If requested :
Manual verification
3 messages:
1st after registration – pending
2nd after verification  payment information
3rd after payment
Email to: registration@ipac26.org

## Slide 10: Mobile App / Info
Notes: Slide 3 – (..) : Content of the presentation
Insert a new slide: Home > “New Slide” and choose a slide Layout:
For Title & Subtitle
For text with bullet points
For Text
For Picture, graphs, visuals
Two columns
Blank
If you want Copy & paste an element from the Clip Board to the particular slide: 1. Click on a box to mark it.
2. Position the mouse pointer on the box frame: Copy! 3. Click on the particular slide: Paste!
How you intend to use the elements is your choice. You can combine the text block style with the background colour in different manner.

## Slide 11: Same as other conferences

## Slide 12: Codes wifis
?